## time log
Name | Date | Task | Start | End | Time spent (hrs)
hpetre | 2018-09-21 | Simulink modelling |  |  | 0.5
hpetre | 2018-09-22 | Simulink modelling | 10.25 | 12.5 | 2.25
| 2018-09-23 | Simulink modelling | 14 | 15 | 1
| 2018-09-30 | Simulink modelling: trying to make model of angle sensor | 20.5 | 22.5 | 2
| 2018-10-01 |  |  |  | 1
| 2018-10-02 | converted model to discrete |  |  | 0.75
| 2018-10-08 | integrating control scheme on board |  |  | 1
| 2018-10-09 | documentation |  |  | 1
| 2018-10-10 | documentation |  |  | 1.5
| 2018-10-11 | documentation |  |  | 1
| 2018-10-21 | solder wires to motors |  |  | 3
|  | read data from imu on kl25z |  |  | 4
| 2018-10-22 | read data from imu on kl25z |  |  | 2.5
solder pins to kl25z for imu function
| 2018-10-23 | solder pins to kl25z for imu function |  |  | 1.5
| 2018-10-24 | read data from imu on kl25z |  |  | 2
| 2018-10-25 | read docs & read data from imu on kl25z |  |  | 1
| 2018-10-29 | connect motor shield to kl25z and motor battery |  |  | 2
| 2018-10-30 | connect motor shield to kl25z and motor battery |  |  | 1.5
| 2018-10-31 | connect motor shield to kl25z and motor battery |  |  | 1.5
| 2018-11-01 | connect motor shield to kl25z and motor battery |  |  | 3
| 2018-11-02 | test motor function |  |  | 5
| 2018-11-03 | test motor function |  |  | 3
| 2018-11-04 | test motor function |  |  | 4

## tasks
design controller in simulink
get parts
2018-10-21 | solder wires to motors
connect wires to motor shield
solder pins to kl25z for motor function
connect motor shield to kl25z and motor battery
read data from imu on kl25z
get imu slave adress
get imu register adress
solder pins to kl25z for imu function
implement control law to control motors with imu input
implement wireless connectivity and control
assemble everything
test
2018-11-27

## useful links
https://learn.sparkfun.com/tutorials/ | useful info I2c etc
http://ozzmaker.com/berryimu/ | imu to board
https://www.youtube.com/watch?v=3230nCz3XQA | solder header pins to board
https://maker.pro/arduino/tutorial/how-to-interface-arduino-and-the-mpu-6050-sensor
https://www.intorobotics.com/accelerometer-gyroscope-and-imu-sensors-tutorials/
https://www.youtube.com/watch?v=jJla0qBJc4Q | mBed Tutorial 8.4: I2C Set up
https://www.youtube.com/watch?v=1MTzhtqj2KQ | mBed Tutorial 8.5: I2C Reading the TCS34725 Spec Sheet
https://os.mbed.com/platforms/KL25Z/ | KL25Z info
https://www.youtube.com/watch?v=M9lZ5Qy5S2s | i2c interface, arduino mpu6050
https://www.instructables.com/id/Arduino-Nano-Control-Brushelss-DC-Motor-With-L9110/ | connect motor controller (test) to board
https://www.electroschematics.com/13797/l9110-motor-driver-primer/ | l9110 motor controller
https://visualgdb.com/tutorials/arm/kinetis/kl25z-rgb-led/